## Tender Summary
🏗 BOQ vs SOR RATE ANALYSIS — TENDER ID: 1264860
BSL/MHDJ/WD-11 — River Bank Protection Work of Tetulia River (Right Bank) Km 3.000–3.300
| Procuring Entity | BWDB — Barishal Water Development Division
| Location | Mehendigonj Upazila, Barishal District
| Agency / SOR | BWDB 2019-20 Schedule of Rates
| Zone | Zone D (Barishal Division)
| Invitation Ref. | 42.01.0600.000.112.07.0001.25-2642, Date: 27/04/2026
| Tender ID | 1264860
| Tender Security | Tk. 61,00,000 (Sixty One Lakh)
| Closing Date | 19-May-2026 14:00
| Work Period | 01-Oct-2026 to 23-Mar-2028
| Report Generated | 24-May-2026 22:47
| Total SOR Amount (BDT) |  | 241865221.7683
| Total Quoted Amount (BDT) |  | 236856068.8497
| Saving vs SOR (BDT) |  | 5009152.9186
| Discount (%) |  | 2.07
📋 QUALIFICATION REQUIREMENTS (TDS)
| Experience (General) | 5 years as Prime/Sub/Mgmt Contractor
| Experience (Specific) | Min 1 contract revetment/bank protection ≥ Tk. 1,210 Lakh (last 5 yrs)
| Annual Turnover (AACT) | Tk. 2,420 Lakh over last 5 financial years
| Financial Resources | Tk. 850 Lakh (liquid/credit line) — Form e-PW3-8
| Min Tender Capacity | Tk. 1,820 Lakh
| Personnel | Project Manager (BSc Civil, 5yr) + JE (BSc, 4yr) + 2 Site Engineers (Diploma)
| Equipment | 4 Concrete Mixers, 4 Vibrators, 3000 Block Forms, 2 Excavators, 4 Engine Boats, 2 Barges
| JV | Allowed — e-PW3-B form, non-judicial stamp Tk. 300

## BOQ Rate Comparison
BOQ vs BWDB SOR RATE COMPARISON — Tender 1264860 — BSL/MHDJ/WD-11
LEGEND: ✅ AT SOR (±1%) ⚠ VARIANCE (1–10%) 🔵 BELOW SOR (>10% discount) 🔴 ABOVE SOR (>10% premium) ¦ Agency: BWDB = Water Dev Board ¦ PWD = Public Works ¦ LGED = Local Gov Eng
# | Item Code | Agency | Work Type | Description of Item | Unit | Quantity | BWDB SOR Rate (BDT) | SOR Amount (BDT) | Quoted Rate (BDT) | Quoted Amount (BDT) | Rate Diff (BDT) | Variance (%) | Status
▶ PRELIMINARIES
1 | 04-180 | BWDB | Preliminaries | Preparation of Site by manually removing all miscellaneous objectionable materials | sqm | 36000 | 43.54 | 1567440 | 30.478 | 1097208 | -13.062 | -30% | BELOW SOR
2 | 01.1.3 | PWD | Preliminaries | Erection and maintenance of semi permanent site office | Each | 1 | 487130 | 487130 | 487130 | 487130 | 0 | 0% | AT SOR
▶ EARTHWORK
3 | 40-920 | BWDB | Earthwork | Earth work in cutting and filling of eroded bank of river, channel etc. ,ditch filling within 50m rest disposed at 100m distance | cum | 3367.55 | 248.87 | 838082.1685 | 199.096 | 670465.7348 | -49.774 | -20% | BELOW SOR
4 | 16-720-10 | BWDB | Earthwork | Filling ditch/pond/channel/khal etc within 1 km along the rive | cum/km | 5178.74 | 173.46 | 898304.2404 | 138.768 | 718643.3923 | -34.692 | -20% | BELOW SOR
5 | 16-720-20 | BWDB | Earthwork | Filling ditch/pond/channel/khal etc within 2 km & above along the rive | cum/km | 5178.74 | 5.31 | 27499.1094 | 4.248 | 21999.2875 | -1.062 | -20% | BELOW SOR
▶ FILTER WORKS
6 | 40-550-30 | BWDB | Filter Works | Supply & Laying Sand filter FM: 1.0 to 1.5 | cum | 193.65 | 1344.22 | 260308.203 | 1008.165 | 195231.1523 | -336.055 | -25% | BELOW SOR
▶ GEO-BAGS / GEOTEXTILE
7 | 40-500-40 | BWDB | Geo-Bags / Geotextile | Geo-tex filter supply and laying, 3mm thickness, 400 g/m2 mass100% Polypropylene Fabric, Thickness=> 3mm | sqm | 3075.86 | 286.16 | 880188.0976 | 228.928 | 704150.4781 | -57.232 | -20% | BELOW SOR
▶ FILTER WORKS
8 | 40-520-20 | BWDB | Filter Works | Jhama chips Well graded between 40mm to 20mm size | cum | 96.4 | 5784.88 | 557662.432 | 4627.904 | 446129.9456 | -1156.976 | -20% | BELOW SOR
9 | 40-520-30 | BWDB | Filter Works | Jhama chips Well graded between 20mm to 5mm size (Combination of sub-item 10 & 30 or 20 & 30 shall be used). | cum | 96.4 | 6285.92 | 605962.688 | 5028.736 | 484770.1504 | -1257.184 | -20% | BELOW SOR
▶ CC BLOCKS & DUMPING
10 | 40-170-40 | BWDB | CC Blocks & Dumping | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 40 cm x 40 cm x 20 cm; 28 days cylinder strength of 10.50 N/mm² | Each | 10440 | 485 | 5063400 | 495 | 5167800 | 10 | 2.06% | VARIANCE
11 | 40-170-06 | BWDB | CC Blocks & Dumping | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 40 cm x 40 cm x 30 cm; 28 days cylinder strength of 9.0 N/mm131 |  | 2043 | 727.51 | 1486302.93 | 745 | 1522035 | 17.49 | 2.4% | VARIANCE
12 | 40-170-25 | BWDB | CC Blocks & Dumping | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 45cm x 45cm x 45cm; 28 days cylinder strength of 9.0 N/mm² | Each | 67291 | 1384.61 | 93171791.51 | 1405 | 94543855 | 20.39 | 1.47% | VARIANCE
13 | 40-170-45 | BWDB | CC Blocks & Dumping | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 35cm x 35cm x 35cm; 28 days cylinder strength of 9.0 N/mm² | Each | 94813 | 650.35 | 61661634.55 | 660 | 62576580 | 9.65 | 1.48% | VARIANCE
▶ GEO-BAGS / GEOTEXTILE
14 | 40-360-10 | BWDB | Geo-Bags / Geotextile | "[Dumping with Barge & Total Station] Geo-bag; inner size:1200mmX 950mm, Outer size: 1250mmX1000mm; Fill vol= 0.1664cum, wt=250 kg. | Each | 58594 | 681.72 | 39944701.68 | 675 | 39550950 | -6.72 | -0.99% | AT SOR
15 | 40-380-10 | BWDB | Geo-Bags / Geotextile | Supplying filling and placing of geo-textile bags 250 Kg | Nos | 4380 | 655.62 | 2871615.6 | 655.62 | 2871615.6 | 0 | 0% | AT SOR
16 | 40-570-10 | BWDB | Geo-Bags / Geotextile | Labour charge for salvaging of Geo-Bags of different sizes including carriage within the site of any protective work with all leads and lifts and stacking in measurable stacks as per direction of Engineer in charge. Salvaging of 250 kg | Nos | 4380 | 34.17 | 149664.6 | 34.17 | 149664.6 | 0 | 0% | AT SOR
17 | 40-320-10 | BWDB | Geo-Bags / Geotextile | Supplying of geo-textile bags (empty) Geo-bag: size= inner:1200mmX 950mm, Outer: 1250mmX1000mm; Geo-fabric thickness=> 3.00mm fill vol= 0.1664cum, wt=250 kg. " | Nos | 2344 | 424.09 | 994066.96 | 424.09 | 994066.96 | 0 | 0% | AT SOR
▶ CC BLOCKS & DUMPING
18 | 40-270-10 | BWDB | CC Blocks & Dumping | Labor charge for Laying C.C. Block .Within 200m. | cum | 439.56 | 1586.93 | 697550.9508 | 1269.544 | 558040.7606 | -317.386 | -20% | BELOW SOR
19 | 40-270-20 | BWDB | CC Blocks & Dumping | Labor charge for Laying C.C. Block .Within 200m. To 500m | cum | 439.56 | 2486.73 | 1093067.0388 | 1989.384 | 874453.631 | -497.346 | -20% | BELOW SOR
20 | 40-300-10 | BWDB | CC Blocks & Dumping | Dumping work of Hard rock/stone/ boulders/C.C blocks/brick blocks/ sand cement blocks over a uniform area from properly positioned flat-top pontoon/barge up to an accuracy of 10cm monitoring with total station.-Within 200m. | cum | 4875.02 | 2463.7 | 12010586.774 | 1970.96 | 9608469.4192 | -492.74 | -20% | BELOW SOR
21 | 40-300-20 | BWDB | CC Blocks & Dumping | Dumping work of Hard rock/stone/ boulders/C.C blocks/brick blocks/ sand cement blocks over a uniform area from properly positioned flat-top pontoon/barge up to an accuracy of 10cm monitoring with total station. - 200m. To 500 m | cum | 4875.02 | 3061.99 | 14927262.4898 | 2449.592 | 11941809.9918 | -612.398 | -20% | BELOW SOR
▶ EARTHWORK
22 | 02-1-2 | PWD | Earthwork | Earth work in excavation in all kinds of soil for foundation trenches | cum | 42.65 | 153 | 6525.45 | 153 | 6525.45 | 0 | 0% | AT SOR
▶ STRUCTURAL CONCRETE
23 | 03.4.2 | PWD | Structural Concrete | Lean / blinding concrete (1:3:6) in foundation | cum | 10.47 | 8971 | 93926.37 | 8971 | 93926.37 | 0 | 0% | AT SOR
24 | PWD07.18.3 | PWD | Structural Concrete | Centering and shuttering, including strutting, propping etc. and removal of form for: Padestals. column, walls | sqm | 39.69 | 508 | 20162.52 | 508 | 20162.52 | 0 | 0% | AT SOR
25 | 08.1.2 | PWD | Structural Concrete | MS Rod | kg | 693.54 | 120 | 83224.8 | 120 | 83224.8 | 0 | 0% | AT SOR
26 | 07.2.2 | PWD | Structural Concrete | RCC Work | cum | 6.67 | 13680 | 91245.6 | 13680 | 91245.6 | 0 | 0% | AT SOR
▶ FINISHING
27 | 3.12.06 | LGED | Finishing | Painting and writing on kilometer post | sqm | 6.16 | 314.54 | 1937.5664 | 314.54 | 1937.5664 | 0 | 0% | AT SOR
▶ ELECTRICAL
28 | 1.02 | LGED | Electrical | Project Profile Signboard: Providing and fixing of typical project profile signboard | sqm | 4.32 | 16755.53 | 72383.8896 | 16755.53 | 72383.8896 | 0 | 0% | AT SOR
▶ FINISHING
29 | 04-3(PWD) | PWD | Finishing | Brick works with first class bricks | cum | 3.51 | 9657 | 33896.07 | 9657 | 33896.07 | 0 | 0% | AT SOR
30 | 06-4-1 | PWD | Finishing | Supplying, fitting and fixing foreign made polished pocelain/ mirror polished homogeneous floor tiles | sqm | 25.45 | 2562 | 65202.9 | 2562 | 65202.9 | 0 | 0% | AT SOR
31 | 06-6-1 | PWD | Finishing | Supplying, fitting and fixing country made glazed wall tiles | sqm | 19.91 | 1311 | 26102.01 | 1311 | 26102.01 | 0 | 0% | AT SOR
32 | 16-1-1(PWD | PWD | Finishing | Exterior standard acrylic emulsion paint | sqm | 662.81 | 261 | 172993.41 | 261 | 172993.41 | 0 | 0% | AT SOR
33 | 15-1-1(PWD) | PWD | Finishing | Minimum 12 mm thick cement sand (F.M. 1.2) plaster | sqm | 9.05 | 297 | 2687.85 | 297 | 2687.85 | 0 | 0% | AT SOR
▶ OTHER
34 | 03.1.1(PWD) | PWD | Other | One layer brick flat soling in foundation | sqm | 9.05 | 607 | 5493.35 | 607 | 5493.35 | 0 | 0% | AT SOR
▶ ELECTRICAL
35 | PWD EM-1.18.1.1.1 | PWD | Electrical | Providing & laying of the following PVC insulated & sheathed cable (NYY) / (XLPE) insulated & PVC sheathed cable | m | 24 | 450 | 10800 | 450 | 10800 | 0 | 0% | AT SOR
36 | PWD EM12.1 | PWD | Electrical | Supplying. installation, testing & commissioning of following capacity solar system (offgrid) for 2 Hrs backup with required quantities of mono /poly crystalline silicon solar PV modules,S | KWp | 3 | 176910 | 530730 | 176910 | 530730 | 0 | 0% | AT SOR
37 | PWD EM-6.8.3.1.1 | PWD | Electrical | STREET LIGHT FITTINGS (LED) Supply & fixing LED street light fittings of following specifications: | Each | 3 | 9225 | 27675 | 9225 | 27675 | 0 | 0% | AT SOR
38 | PWD EM3.2.4 | PWD | Electrical | G. I. POLE Providing following seamless Cl pole | Each | 3 | 16550 | 49650 | 16550 | 49650 | 0 | 0% | AT SOR
39 | PWD EM3.10.1 | PWD | Electrical | STAY Providing and fixing following pole stay made of stranded Gl. wires complete with anchor plate of size 304.8 mm x 304.8 mm x 6.35 mm | Each | 3 | 1841 | 5523 | 1841 | 5523 | 0 | 0% | AT SOR
40 | PWD EM3.17.1 | PWD | Electrical | SERVICE BRACKET Providing and fixing of 1524 mm (5') long 25.40 mm (1,') dia Gt. Pipe service bracket complete with I no. of Gl bend 2 nos. fixing clamps of 38.l0 mm x 6.35 mm (I.5''x1/4'') size iron flat bar bolts. nuts etc. complete as required | Each | 3 | 1201 | 3603 | 1201 | 3603 | 0 | 0% | AT SOR
41 | PWD EM4.9.2 | PWD | Electrical | BOARD Supplying and fixing of almirah type 18 SWG metal board of depth 228mm (6'') duly painted | Each | 3 | 17547 | 52641 | 17547 | 52641 | 0 | 0% | AT SOR
42 | PWD EM-4.4.1.1 | PWD | Electrical | CIRCUlT BREAKER (SPMCI]) Providing & fixing on a prepared board 250 yolt grade following single pole miniature circuil breaker (SpMCBs) having minimum breaking capacity 6-KA / I0 KA with thermal over-current and instantaneous electromagnetic short circuit release provision as per BDS IEC and IEC /VDE / NEMA / BS / JIS standard. SPMCBs accepted / approved by the Ergireer-in-charge. 5 - .{0 Amps (minimum 6 KA) MCB | Each | 3 | 779 | 2337 | 779 | 2337 | 0 | 0% | AT SOR
43 | PWD EM4.19.1 | PWD | Electrical | EARTHING Earthing the electrical installation with 40 mm ( 1.5'') dia c.l. pipe (earth electrode) having 6.35 mm. dia hole | Each | 3 | 24786 | 74358 | 24786 | 74358 | 0 | 0% | AT SOR
▶ STRUCTURAL CONCRETE
44 | 03.5.1(PWD) | PWD | Structural Concrete | Mass concrete (1:2:4) in foundation or in floor with cement | cum | 1.79 | 10224 | 18300.96 | 10224 | 18300.96 | 0 | 0% | AT SOR
▶ LABOUR
45 | 80-305 | BWDB | Labour | Head Man | Day | 18 | 800 | 14400 | 800 | 14400 | 0 | 0% | AT SOR
46 | 80-370 | BWDB | Labour | Labour-Skilled | Day | 180 | 600 | 108000 | 600 | 108000 | 0 | 0% | AT SOR
47 | 80-375 | BWDB | Labour | Labour-unskilled | Day | 180 | 540 | 97200 | 540 | 97200 | 0 | 0% | AT SOR
GRAND TOTAL | [7 empty] | 241865221.7683 |  | 236856068.8497 | -5009152.9186 | -2.071%

## Work Type Summary
WORK TYPE — COST SUMMARY & BREAKDOWN — Tender 1264860
Work Type | Items | SOR Amount (BDT) | Quoted Amount (BDT) | Saving (BDT) | Discount (%) | % of Quoted Total
CC Blocks & Dumping | 8 | 190111596.2434 | 186793043.8027 | 3318552.4407 | 1.746% | 78.86%
Geo-Bags / Geotextile | 5 | 44840236.9376 | 44270447.6381 | 569789.2995 | 1.271% | 18.69%
Preliminaries | 2 | 2054570 | 1584338 | 470232 | 22.89% | 0.6689%
Earthwork | 4 | 1770410.9683 | 1417633.8646 | 352777.1037 | 19.93% | 0.5985%
Filter Works | 3 | 1423933.323 | 1126131.2482 | 297802.0747 | 20.91% | 0.4754%
Electrical | 10 | 829700.8896 | 829700.8896 | 0 | 0% | 0.3503%
Structural Concrete | 5 | 306860.25 | 306860.25 | 0 | 0% | 0.1296%
Finishing | 6 | 302819.8064 | 302819.8064 | 0 | 0% | 0.1278%
Labour | 3 | 219600 | 219600 | 0 | 0% | 0.09271%
Other | 1 | 5493.35 | 5493.35 | 0 | 0% | 0.002319%
TOTAL | 47 | 241865221.7683 | 236856068.8497 | 5009152.9186 | -2.071% | 100%

## Rate Detail & Flags
RATE DETAIL — FLAGGED ITEMS FOR REVIEW / NEGOTIATION
# | Code | Agency | Description | Unit | Qty | SOR Rate | Quoted Rate | Saving/Unit | Total Saving | Status
1 | 04-180 | BWDB | Preparation of Site by manually removing all miscellaneous objectionable materials | sqm | 36000 | 43.54 | 30.478 | 13.062 | 470232 | BELOW SOR
2 | 01.1.3 | PWD | Erection and maintenance of semi permanent site office | Each | 1 | 487130 | 487130 | 0 | 0 | AT SOR
3 | 40-920 | BWDB | Earth work in cutting and filling of eroded bank of river, channel etc. ,ditch filling within 50m rest disposed at 100m distance | cum | 3367.55 | 248.87 | 199.096 | 49.774 | 167616.4337 | BELOW SOR
4 | 16-720-10 | BWDB | Filling ditch/pond/channel/khal etc within 1 km along the rive | cum/km | 5178.74 | 173.46 | 138.768 | 34.692 | 179660.8481 | BELOW SOR
5 | 16-720-20 | BWDB | Filling ditch/pond/channel/khal etc within 2 km & above along the rive | cum/km | 5178.74 | 5.31 | 4.248 | 1.062 | 5499.8219 | BELOW SOR
6 | 40-550-30 | BWDB | Supply & Laying Sand filter FM: 1.0 to 1.5 | cum | 193.65 | 1344.22 | 1008.165 | 336.055 | 65077.0508 | BELOW SOR
7 | 40-500-40 | BWDB | Geo-tex filter supply and laying, 3mm thickness, 400 g/m2 mass100% Polypropylene Fabric, Thickness=> 3mm | sqm | 3075.86 | 286.16 | 228.928 | 57.232 | 176037.6195 | BELOW SOR
8 | 40-520-20 | BWDB | Jhama chips Well graded between 40mm to 20mm size | cum | 96.4 | 5784.88 | 4627.904 | 1156.976 | 111532.4864 | BELOW SOR
9 | 40-520-30 | BWDB | Jhama chips Well graded between 20mm to 5mm size (Combination of sub-item 10 & 30 or 20 & 30 shall be used). | cum | 96.4 | 6285.92 | 5028.736 | 1257.184 | 121192.5376 | BELOW SOR
10 | 40-170-40 | BWDB | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 40 cm x 40 cm x 20 cm; 28 days cylinder strength of 10.50 N/mm² | Each | 10440 | 485 | 495 | -10 | -104400 | VARIANCE
11 | 40-170-06 | BWDB | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 40 cm x 40 cm x 30 cm; 28 days cylinder strength of 9.0 N/mm131 |  | 2043 | 727.51 | 745 | -17.49 | -35732.07 | VARIANCE
12 | 40-170-25 | BWDB | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 45cm x 45cm x 45cm; 28 days cylinder strength of 9.0 N/mm² | Each | 67291 | 1384.61 | 1405 | -20.39 | -1372063.49 | VARIANCE
13 | 40-170-45 | BWDB | C.C blocks(1:3:5.5), FM>=1.5, Stone chips 40mm, Block size 35cm x 35cm x 35cm; 28 days cylinder strength of 9.0 N/mm² | Each | 94813 | 650.35 | 660 | -9.65 | -914945.45 | VARIANCE
14 | 40-360-10 | BWDB | "[Dumping with Barge & Total Station] Geo-bag; inner size:1200mmX 950mm, Outer size: 1250mmX1000mm; Fill vol= 0.1664cum, wt=250 kg. | Each | 58594 | 681.72 | 675 | 6.72 | 393751.68 | AT SOR
15 | 40-380-10 | BWDB | Supplying filling and placing of geo-textile bags 250 Kg | Nos | 4380 | 655.62 | 655.62 | 0 | 0 | AT SOR
16 | 40-570-10 | BWDB | Labour charge for salvaging of Geo-Bags of different sizes including carriage within the site of any protective work with all leads and lifts and stacking in measurable stacks as per direction of Engineer in charge. Salvaging of 250 kg | Nos | 4380 | 34.17 | 34.17 | 0 | 0 | AT SOR
17 | 40-320-10 | BWDB | Supplying of geo-textile bags (empty) Geo-bag: size= inner:1200mmX 950mm, Outer: 1250mmX1000mm; Geo-fabric thickness=> 3.00mm fill vol= 0.1664cum, wt=250 kg. " | Nos | 2344 | 424.09 | 424.09 | 0 | 0 | AT SOR
18 | 40-270-10 | BWDB | Labor charge for Laying C.C. Block .Within 200m. | cum | 439.56 | 1586.93 | 1269.544 | 317.386 | 139510.1902 | BELOW SOR
19 | 40-270-20 | BWDB | Labor charge for Laying C.C. Block .Within 200m. To 500m | cum | 439.56 | 2486.73 | 1989.384 | 497.346 | 218613.4078 | BELOW SOR
20 | 40-300-10 | BWDB | Dumping work of Hard rock/stone/ boulders/C.C blocks/brick blocks/ sand cement blocks over a uniform area from properly positioned flat-top pontoon/barge up to an accuracy of 10cm monitoring with total station.-Within 200m. | cum | 4875.02 | 2463.7 | 1970.96 | 492.74 | 2402117.3548 | BELOW SOR
21 | 40-300-20 | BWDB | Dumping work of Hard rock/stone/ boulders/C.C blocks/brick blocks/ sand cement blocks over a uniform area from properly positioned flat-top pontoon/barge up to an accuracy of 10cm monitoring with total station. - 200m. To 500 m | cum | 4875.02 | 3061.99 | 2449.592 | 612.398 | 2985452.498 | BELOW SOR
22 | 02-1-2 | PWD | Earth work in excavation in all kinds of soil for foundation trenches | cum | 42.65 | 153 | 153 | 0 | 0 | AT SOR
23 | 03.4.2 | PWD | Lean / blinding concrete (1:3:6) in foundation | cum | 10.47 | 8971 | 8971 | 0 | 0 | AT SOR
24 | PWD07.18.3 | PWD | Centering and shuttering, including strutting, propping etc. and removal of form for: Padestals. column, walls | sqm | 39.69 | 508 | 508 | 0 | 0 | AT SOR
25 | 08.1.2 | PWD | MS Rod | kg | 693.54 | 120 | 120 | 0 | 0 | AT SOR
26 | 07.2.2 | PWD | RCC Work | cum | 6.67 | 13680 | 13680 | 0 | 0 | AT SOR
27 | 3.12.06 | LGED | Painting and writing on kilometer post | sqm | 6.16 | 314.54 | 314.54 | 0 | 0 | AT SOR
28 | 1.02 | LGED | Project Profile Signboard: Providing and fixing of typical project profile signboard | sqm | 4.32 | 16755.53 | 16755.53 | 0 | 0 | AT SOR
29 | 04-3(PWD) | PWD | Brick works with first class bricks | cum | 3.51 | 9657 | 9657 | 0 | 0 | AT SOR
30 | 06-4-1 | PWD | Supplying, fitting and fixing foreign made polished pocelain/ mirror polished homogeneous floor tiles | sqm | 25.45 | 2562 | 2562 | 0 | 0 | AT SOR
31 | 06-6-1 | PWD | Supplying, fitting and fixing country made glazed wall tiles | sqm | 19.91 | 1311 | 1311 | 0 | 0 | AT SOR
32 | 16-1-1(PWD | PWD | Exterior standard acrylic emulsion paint | sqm | 662.81 | 261 | 261 | 0 | 0 | AT SOR
33 | 15-1-1(PWD) | PWD | Minimum 12 mm thick cement sand (F.M. 1.2) plaster | sqm | 9.05 | 297 | 297 | 0 | 0 | AT SOR
34 | 03.1.1(PWD) | PWD | One layer brick flat soling in foundation | sqm | 9.05 | 607 | 607 | 0 | 0 | AT SOR
35 | PWD EM-1.18.1.1.1 | PWD | Providing & laying of the following PVC insulated & sheathed cable (NYY) / (XLPE) insulated & PVC sheathed cable | m | 24 | 450 | 450 | 0 | 0 | AT SOR
36 | PWD EM12.1 | PWD | Supplying. installation, testing & commissioning of following capacity solar system (offgrid) for 2 Hrs backup with required quantities of mono /poly crystalline silicon solar PV modules,S | KWp | 3 | 176910 | 176910 | 0 | 0 | AT SOR
37 | PWD EM-6.8.3.1.1 | PWD | STREET LIGHT FITTINGS (LED) Supply & fixing LED street light fittings of following specifications: | Each | 3 | 9225 | 9225 | 0 | 0 | AT SOR
38 | PWD EM3.2.4 | PWD | G. I. POLE Providing following seamless Cl pole | Each | 3 | 16550 | 16550 | 0 | 0 | AT SOR
39 | PWD EM3.10.1 | PWD | STAY Providing and fixing following pole stay made of stranded Gl. wires complete with anchor plate of size 304.8 mm x 304.8 mm x 6.35 mm | Each | 3 | 1841 | 1841 | 0 | 0 | AT SOR
40 | PWD EM3.17.1 | PWD | SERVICE BRACKET Providing and fixing of 1524 mm (5') long 25.40 mm (1,') dia Gt. Pipe service bracket complete with I no. of Gl bend 2 nos. fixing clamps of 38.l0 mm x 6.35 mm (I.5''x1/4'') size iron flat bar bolts. nuts etc. complete as required | Each | 3 | 1201 | 1201 | 0 | 0 | AT SOR
41 | PWD EM4.9.2 | PWD | BOARD Supplying and fixing of almirah type 18 SWG metal board of depth 228mm (6'') duly painted | Each | 3 | 17547 | 17547 | 0 | 0 | AT SOR
42 | PWD EM-4.4.1.1 | PWD | CIRCUlT BREAKER (SPMCI]) Providing & fixing on a prepared board 250 yolt grade following single pole miniature circuil breaker (SpMCBs) having minimum breaking capacity 6-KA / I0 KA with thermal over-current and instantaneous electromagnetic short circuit release provision as per BDS IEC and IEC /VDE / NEMA / BS / JIS standard. SPMCBs accepted / approved by the Ergireer-in-charge. 5 - .{0 Amps (minimum 6 KA) MCB | Each | 3 | 779 | 779 | 0 | 0 | AT SOR
43 | PWD EM4.19.1 | PWD | EARTHING Earthing the electrical installation with 40 mm ( 1.5'') dia c.l. pipe (earth electrode) having 6.35 mm. dia hole | Each | 3 | 24786 | 24786 | 0 | 0 | AT SOR
44 | 03.5.1(PWD) | PWD | Mass concrete (1:2:4) in foundation or in floor with cement | cum | 1.79 | 10224 | 10224 | 0 | 0 | AT SOR
45 | 80-305 | BWDB | Head Man | Day | 18 | 800 | 800 | 0 | 0 | AT SOR
46 | 80-370 | BWDB | Labour-Skilled | Day | 180 | 600 | 600 | 0 | 0 | AT SOR
47 | 80-375 | BWDB | Labour-unskilled | Day | 180 | 540 | 540 | 0 | 0 | AT SOR

## Financial Check
FINANCIAL QUALIFICATION CHECKLIST — Hassan & Brothers JV
| Criterion | Required | Our Figure | Remarks | Status
| Avg Annual Construction Turnover | Tk. 2,420 Lakh | See audit/turnover cert. | AACT ≥ 2420 Lakh over 5 yrs | ⚠ Verify
| Min Financial Resource (Line of Credit) | Tk. 850 Lakh | NCC Bank — Tk. 850 Lakh LoC | Form e-PW3-8 submitted | ✅ OK
| Tender Capacity (A×N×1.25 - B) | Tk. 1,820 Lakh | Calculate from max annual work | N = completion years | ⚠ Verify
| Tender Security | Tk. 61 Lakh (BG) | BG from NCC Bank | Form e-PW3-7 | ✅ OK
| Experience (Specific) | 1 contract ≥ Tk. 1,210 Lakh | River bank protection work | Must submit completion cert. | ⚠ Verify
| JV Agreement | e-PW3-B, Tk. 300 stamp | HB-SRT JV deed submitted | Non-judicial stamp verified | ✅ OK
| Tax Documents | TIN + IT Return 2024-25 + VAT | All submitted | Income tax year: 2024-25 | ✅ OK
| Ongoing Works Declaration | Signed list required | Must declare all ongoing works | JV % share on each cert. | ⚠ Verify