## 1242557
Tender ID: 1242557 |  | WORK SCHEDULE | [6 empty] | Package: NDR-44/Patiya/Amilaish/SW/2025-26
Name of Work: “Strengthening of existing bank protection work along the Sangu River from Km 0.000 to Km 0.100 (=100.00 m) to safeguard Amilaish Village Road in Amilaish Union, Satkania Upazila, Chattogram District in connection with "Operational Expenditure for Repair and Maintenance of Goods and Services (Economic Code-3258137)" under Chattogram WD Division-I, BWDB, Chattogram, during the year 2025-2026.” (e-Tender ID: 1242557, Package No: NDR-44/Patiya/Amilaish/SW/2025-26)
Sl. No. | Activity | 2026 | [8 empty] | 2027
|  | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
i | Site Preparation & Mobilization.
ii | Procurement of Man power, Equipment, Materials & etc.
iii | Earthworks
iv | Dumping & Placing Geo-Textile Bags
v | Manufacturing of C.C. Blocks
vi | Supply of Sand Filter, Geo-Textile Filter, Khoa filter etc.
vii | Dumping & Placing C.C Blocks
viii | CC work
ix | De-mobilization & Site handover
Mahmudul Hassan
Proprietor